## 1.WBS with Gantt Chartt Task1&2
Work Breakdown Structure (WBS) Gantt Chart:
Here’s is a link to the Gantt chart: | WBS Gantt Chart Task 1 and 2

## 2.WBS Task1 Requirement testing
Here’s a more detailed Work Breakdown Structure (WBS) for the testing activity in Task 1 and the next worksheet has the same for the 4 New Use Cases provided in Task 2:
Work Breakdown Structure (New requirements in Task 1)
Task Serial Number | Testing Activity Task | Subtask Serial Number | Subtask | Task Description | Estimated/Planned Time | Actual Time | Assignee
1.1.1 | Test Data Preparation | 1.1.1.1 | Create Table: Define Parameters and fields | Create a table in the database with fields corresponding to the search parameters. | 1 hour | TBD | TBD
|  | 1.1.1.2 | Test Case Creation | Populate the table with valid and effective test data for various scenarios. | 1 hour | TBD | TBD
1.1.2 | Test Case Creation | 1.1.2.1 | Positive Test Cases Creation | Create test cases that cover all the requirements under normal conditions. | 2 day | TBD | TBD
|  | 1.1.2.2 | Negative Test Cases Creation | Create test cases that cover all the requirements under abnormal or unexpected conditions. | 1 day | TBD | TBD
1.1.3 | Test Execution | 1.1.3.1 | Positive Test Cases Execution | Execute all the positive test cases and record the results. | 2 days | TBD | TBD
|  | 1.1.3.2 | Negative Test Cases Execution | Execute all the negative test cases and record the results. | 2 days | TBD | TBD
1.1.4 | Bug Reporting and Retesting | 1.1.4.1 | Bug Reporting & Retesting | Document any bugs or issues found during testing and report them to the development team. Once the reported issues have been fixed, retest to ensure the fixes work as expected. | 2 days | TBD | TBD
Final Time Sheet
Task Serial Number | Estimated Time For Each Task
1.1.1 | 2 hours
1.1.2 | 3 days
1.1.3 | 4 days
1.1.4 | 2 days
Total Estimated Time for Complete Testing Activity | 9.5 Days
Task Serial Number | Actual Time spent on each task
1.1.1 | TBD
1.1.2 | TBD
1.1.3 | TBD
1.1.4 | TBD
Total Actual Time spent on the Complete Activity | TBD

## 3.WBS Task 2 New requirements
Work Breakdown Structure (New requirements in Task 1)
Task Serial Number | Testing Activity Task | Subtask Serial Number | Subtask | Task Description | Estimated/Planned Time | Actual Time | Assignee
2.1.1 | User Registration Testing | 2.1.1.1 | Test case creation | Create test cases that cover all the requirements based on the use case and user stories shared by customer. | 1 day | TBD | TBD
|  | 2.1.1.2 | Test execution | Execute all the use case related positive and negative test cases created in the above sub task, and record the results. | 1 day | TBD | TBD
|  | 2.1.1.3 | Bug reporting and retesting | Document any bugs or issues found during testing and report them to the development team. Once the reported issues have been fixed, retest to ensure the fixes work as expected. | 1 day
2.1.2 | Booking of Office Place Testing | 2.1.2.1 | Test case creation | Create test cases that cover all the requirements based on the use case and user stories shared by customer. | 1 day | TBD | TBD
|  | 2.1.2.2 | Test execution | Execute all the use case related positive and negative test cases created in the above sub task, and record the results. | 1 day | TBD | TBD
|  | 2.1.2.3 | Bug reporting and retesting | Document any bugs or issues found during testing and report them to the development team. Once the reported issues have been fixed, retest to ensure the fixes work as expected. | 1 day
2.1.3 | User Roles Testing | 2.1.3.1 | Test case creation | Create test cases that cover all the requirements based on the use case and user stories shared by customer. | 1 day | TBD | TBD
|  | 2.1.3.2 | Test execution | Execute all the use case related positive and negative test cases created in the above sub task, and record the results. | 1 day | TBD | TBD
|  | 2.1.3.3 | Bug reporting and retesting | Create test cases that cover all the requirements based on the use case and user stories shared by customer. | 1 day
2.1.4 | Mobile Application Testing | 2.1.4.1 | Test case creation | Document any bugs or issues found during testing and report them to the development team. Once the reported issues have been fixed, retest to ensure the fixes work as expected. | 1 day | TBD | TBD
|  | 2.1.4.2 | Test execution | Execute all the use case related positive and negative test cases created in the above sub task, and record the results. | 3 days
|  | 2.1.4.3 | Bug reporting and retesting | Document any bugs or issues found during testing and report them to the development team. Once the reported issues have been fixed, retest to ensure the fixes work as expected. | 1 day
Final Time Sheet
Task Serial Number | Estimated Time For Each Task
2.1.1 | 3 days
2.1.2 | 3 days
2.1.3 | 3 days
2.1.4 | 5 days
Total Estimated Time for Complete Testing Activity | 14 Days
Task Serial Number | Actual Time spent on each task
2.1.1 | TBD
2.1.2 | TBD
2.1.3 | TBD
2.1.4 | TBD
Total Actual Time spent on the Complete Activity | TBD

## 4.Assumptions & Testing Quality
Assumptions: • The testing team is familiar with the technology stack used in development. • Necessary testing tools and environments are available or will be provided. Expected Level of Quality: • All new features including user registration, booking system, user roles, and mobile application should be fully functional without major bugs. • The system should handle errors gracefully, providing useful feedback to users. • Security aspects especially related to user data protection should be thoroughly tested to ensure data integrity and privacy.

## 5.Test Plan & Strategy-New Reqs
Test Plan & Strategy for New Features/Use Cases-
The task involves planning and executing a testing strategy for a new increment of an application. The new features to be tested are directly derived from the user stories provided by the customer: 1. User Registration: As per the user story, users want to register into the system to view their booked working places. The testing should ensure that the registration process is smooth and secure. 2. Booking of Office Places: Users want to book available working places for future use and have the ability to cancel their bookings. The testing should validate that the booking and cancellation functionalities work as expected. 3. User Roles: There are two roles - user and office manager. Users want to use a mobile application for system usage at any time. Office managers want to manage working places and create new ones. The testing should confirm that the roles are implemented correctly and the associated functionalities work as intended. 4. Native Mobile Application: Users want to use a mobile application for system usage. The testing should ensure that the mobile application is user-friendly, functional, and provides a seamless experience.
The testing activities can be summarized in a process as follows: 1. Requirement Analysis: Understand and analyse the new features and user stories. 2. Test Planning: Develop a test plan detailing the testing approach, resources, test environment, and schedule of testing activities. 3. Test Case Development: Create detailed, comprehensive, and well-structured test cases for each user story. 4. Test Execution: Execute the test cases and report any bugs or issues identified. 5. Regression Testing: Ensure that the new features have not affected the existing functionalities of the application. 6. Performance Testing: Check the application’s performance, especially under heavy load, given the addition of new features. 7. Usability Testing: Verify the application’s user-friendliness and accessibility, particularly for the new user roles and the mobile application.
The evaluation of strategy elaboration and estimation skills will be based on the following: 1. Comprehensiveness: All the assumptions used in planning/estimation should be clearly listed. 2. Clarity: A clear vision of the expected level of quality should be provided. 3. Accuracy: The estimated time and resources should align closely with the actual ones. 4. Efficiency: The strategy should aim to identify maximum defects with optimal resources and time. 5. Effectiveness: The strategy should ensure that the application meets its intended purpose and user expectations.